## Slide 1
Battery Bank 90G15
13-3G-FLM017
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 08-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Damon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Replace one battery bank in LC2104 Los Patios
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Feb-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 26-Apr-13 |  | 
Kick Off | 27-Apr-13 | 27-Apr-13 |  | 
Start project | 28-Apr-13 | 07-Aug-13 |  | 
On production | 08-Aug-13 | 08-Aug-13 |  | 
Closure | 08-Aug.13. | 08-Aug-13 |  | 

## Slide 2
HVAC 5TR
13-3G-FLM018
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 08-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Increase the capacity HVAC 5TR the cooling capacity to mitigate the thermal load increase caused IDEN by network growing. Locations affected: Guasave, Magisterio, Valle Real, Saguaro, Frontera, Tecnologico, Anahuac, Hilton, Comercial Fiesta and Zona Indistrial.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 03-Mar-13 | 22-Mar-13 | Closed
PO Date | 04-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 26-Apr-13 |  | 
Kick Off | 27-Apr-13 | 27-Apr-13 |  | 
Start project | 28-Apr-13 | 07-Aug-13 |  | 
On production | 08-Aug-13 | 08-Aug-13 |  | 
Closure | 08-Aug-13 | 08-Aug-13 |  | 

## Slide 3
APM30 Protection
13-3G-FL010
Project Title/ID
Start Date: 25-Feb-13
Completion Date: 14-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Protect 83 outdoor site to prevent damage or theft of installed equipment. Install 83 metal protections in APM30 and 83 metal protection in Himmel cabinet.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 25-Feb-13 | 28-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 01-Mar-13 | 06-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 07-Mar-13 | 15-Mar-13 | 22-Mar-13 | Closed
PO Date | 16-Mar-13 | 03-May-13 |  | Delay
Delivery equipment Date | 04-May-13 | 08-May-13 |  | 
Kick Off | 09-May-13 | 15-May-13 |  | 
Start project | 16-May-13 | 13-Jul-13 |  | 
On production | 14-Jul-13 | 13-Aug-13 |  | 
Closure | 14-Aug-13 | 14-Aug-13 |  | 

## Slide 4
Civil Work Build Dam
13-3G-FL011
Project Title/ID
Start Date: 25-Feb-13
Completion Date: 29-Apr-13
Timeline / ETC
Issues / Risks
Description / Comments
Construction service in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Construction of DAM to prevent water damage due to site flooding. With this DAM construction we reduce the risk of service impact during heavy rains & storms.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 25-Feb-13 | 27-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 28-Feb-13 | 06-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 07-Mar-13 | 15-Mar-13 | 22-Mar-13 | Closed
PO Date | 16-Mar-13 | 16-Mar-13 |  | Delay
Delivery equipment Date | 16-Mar-13 | 20-Mar-13 |  | 
Kick Off | 21-Mar-13 | 22-Mar-13 |  | 
Start project | 23-Mar-13 | 13-Apr-13 |  | 
On production | 14-Apr-13 | 28-Apr-13 |  | 
Closure | 29-Apr-13 | 29-Apr-13 |  | 

## Slide 5
Generator 35 KW & TS
13-3G-FL013
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 03-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Installation services and spare in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Installation of 3 standby generator in critical sites (Tijuanelas, Valladolid, Yalcoba), installed in flood-prone area or highway
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Mar-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Mar-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 30-Apr-13 |  | 
Kick Off | 02-May-13 | 04-May-13 |  | 
Start project | 05-May-13 | 02-Aug-13 |  | 
On production | 03-Aug-13 | 03-Aug-13 |  | 
Closure | 03-Aug-13 | 03-Aug-13 |  | 

## Slide 6
Lighting protector
13-3G-FL014
Project Title/ID
Start Date: 25-Feb-13
Completion Date: 14-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Reinforcement with installation 0f 14 Lighting protector on site that historically had been the most affected by thunder storm and lighting strikes in Campeche Market.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 25-Feb-13 | 28-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 01-Mar-13 | 06-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 07-Mar-13 | 15-Mar-13 | 22-Mar-13 | Closed
PO Date | 16-Mar-13 | 03-May-13 |  | Delay
Delivery equipment Date | 04-May-13 | 04-May-13 |  | 
Kick Off | 04.May-13 | 15-May-13 |  | 
Start project | 16-May-13 | 01-Jul-13 |  | 
On production | 02-Jul-13 | 13-Jul-13 |  | 
Closure | 14-Jul-13 | 14-Jul-13 |  | 

## Slide 7
Generator 20 KW mobile
13-3G-FL016
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 03-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Acquire portable generator (20 Kw) in order to attend efficiently the energy failure events we need some small power generators that manage the power consumption that the Node B.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Mar-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 30-Apr-13 |  | 
Kick Off | 02-May-13 | 04-May-13 |  | 
Start project | 05-May-13 | 02-Aug-13 |  | 
On production | 03-Aug-13 | 03-Aug-13 |  | 
Closure | 03-Aug-13 | 03-Aug-13 |  | 

## Slide 8
Batt. Bank 90G15 Backup Increase
13-3G-FL015
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 03-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Installation of 41 second batt stack to ensure backup power for 4 hours at Node B (3G), to increase the availability of resources, call traffic and network performance in sites during AC fail, blackout and contingencies.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Mar-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 30-Apr-13 |  | 
Kick Off | 02-May-13 | 04-May-13 |  | 
Start project | 05-May-13 | 02-Aug-13 |  | 
On production | 03-Aug-13 | 03-Aug-13 |  | 
Closure | 03-Aug-13 | 03-Aug-13 |  | 

## Slide 9
HVAC 5 TR Capacity
13-3G-FL017
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 03-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Increase the cooler capacity to mitigate the thermal load increase caused by 2G growing and 3G recent installation in 17 sites with multi-tech.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Mar-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 30-Apr-13 |  | 
Kick Off | 02-May-13 | 04-May-13 |  | 
Start project | 05-May-13 | 02-Aug-13 |  | 
On production | 03-Aug-13 | 03-Aug-13 |  | 
Closure | 03-Aug-13 | 03-Aug-13 |  | 

## Slide 10
Battery Bank 90G15 replace damage – DC Power Plant
13-3G-FL018
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 03-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Replace of 14 damage Batt Stack to guarantee backup for 4 hours in 3G Sites (Collocation)
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Mar-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 30-Apr-13 |  | 
Kick Off | 02-May-13 | 04-May-13 |  | 
Start project | 05-May-13 | 02-Aug-13 |  | 
On production | 03-Aug-13 | 03-Aug-13 |  | 
Closure | 03-Aug-13 | 03-Aug-13 |  | 

## Slide 11
HVAC Replacement
13-3G-FL019
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 03-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Replace 15 HVAC in sites near to the coast. Severe weather conditions cause failures into HVAC equipment´s such as saltpeter and corrosion. The change of this equipment is necessary in order to reduce fails and problems of performance due to HVAC failures.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Mar-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 30-Apr-13 |  | 
Kick Off | 02-May-13 | 04-May-13 |  | 
Start project | 05-May-13 | 02-Aug-13 |  | 
On production | 03-Aug-13 | 03-Aug-13 |  | 
Closure | 03-Aug-13 | 03-Aug-13 |  | 

## Slide 12
Battery Bank 90G15 contingencies
13-3G-FL020
Project Title/ID
Start Date: 20-Feb-13
Completion Date: 03-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
To acquire 30 Battery Banks in reserve and to install in case of theft or vandalism. Also to replace out of spec battery banks when encountered.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 23-Feb-13 | 23-Feb-13 | 22-Mar-13 | Closed
Requisition Date | 23-Feb-13 | 04-Mar-13 | 22-Mar-13 | Closed
PO Date | 05-Mar-13 | 22-Apr-13 |  | Delay
Delivery equipment Date | 23-Apr-13 | 30-Apr-13 |  | 
Kick Off | 02-May-13 | 04-Apr-13 |  | 
Start project | 05-May-13 | 02-Aug-13 |  | 
On production | 03-Aug-13 | 03-Aug-13 |  | 
Closure | 03-Aug-13 | 03-Aug-13 |  | 

## Slide 13
Rectifier EPW30-48A Model
13-3G-FL021
Project Title/ID
Start Date: 24-Feb-13
Completion Date: 19-Jun-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Acquire 22 additional rectifiers model EPW30-48A as spare stock to support failures and damage at DC power plant installed in 3G sites (Aggregator, MW Hub Site, Node B) in order to guarantee mean time to store.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 24-Feb-13 | 28-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 01-Mar-13 | 06-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 07-Mar-13 | 15-Mar-13 | 22-Mar-13 | Closed
PO Date | 16-Mar-13 | 03-May-13 |  | Delay
Delivery equipment Date | 04-May-13 | 12-May-13 |  | 
Kick Off | 13-May-13 | 18-May-13 |  | 
Start project | 19-May-13 | 08-Jun-13 |  | 
On production | 09-Jun-13 | 18-Jun-13 |  | 
Closure | 19-Jun-13 | 19-Jun-13 |  | 

## Slide 14
Swap DC Pover Plant (Spare recovery)
13-3G-FL022
Project Title/ID
Start Date: 24-Feb-13
Completion Date: 30-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Spares in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Replace the current EOL DC Power Plant in 22 sites with the new technology. Generate spares for like EOL Plants currently supporting IDEN/3G Sites in Mexico.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 24-Feb-13 | 28-Feb-13 | 22-Mar-13 | Closed
Product register in Oracle | 01-Mar-13 | 06-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 07-Mar-13 | 15-Mar-13 | 22-Mar-13 | Closed
PO Date | 16-Mar-13 | 29-May-13 |  | On going
Delivery equipment Date | 30-May-13 | 01-Jun-13 |  | 
Kick Off | 02-Jun-13 | 05-Jun-13 |  | 
Start project | 06-Jun-13 | 14-Jun-13 |  | 
On production | 15-Jul-13 | 29-Jul-13 |  | 
Closure | 30-Jul-13 | 30-Jul-13 |  | 

## Slide 15
VMSC Erlang Licenses
13-3G-COR010
Project Title/ID
Start Date: 25-Feb-13
Completion Date: 29-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Licenses in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Increase the licenses VMSC Erlang in the CORE equipment to Guadalajara, Tlalnepantla, Merida, Monterrey y Tijuana.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 25-Feb-13 | 13-Mar-13 | 22-Mar-13 | Closed
Product register in Oracle | 14-Mar-13 | 27-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 28-Mar-13 | 10-Apr-13 | 22-Mar-13 | Closed
PO Date | 11-Apr-13 | 16-Apr-13 |  | Delay
Delivery equipment Date | 17-Apr-13 | 09-Jun-13 |  | 
Kick Off | 10-Jun-13 | 17-Jun-13 |  | 
Start project | 18-Jun-13 | 21-Jun-13 |  | 
On production | 22-Jul-13 | 28-Jul-13 |  | 
Closure | 29-Jul-13 | 29-Jul-13 |  | 

## Slide 16
VMGW Erlang Licenses
13-3G-COR011
Project Title/ID
Start Date: 25-Feb-13
Completion Date: 29-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Licenses in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Increase the licenses VMGW Erlang on the CORE equipment to 24 markets.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 25-Feb-13 | 13-Mar-13 | 22-Mar-13 | Closed
Product register in Oracle | 14-Mar-13 | 27-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 28-Mar-13 | 10-Apr-10 | 22-Mar-13 | Closed
PO Date | 11-Apr-13 | 16-Apr-10 |  | Delay
Delivery equipment Date | 17-Apr-13 | 09-Jun-10 |  | 
Kick Off | 10-Jun-13 | 17-Jun-10 |  | 
Start project | 18-Jun-13 | 21-Jul-10 |  | 
On production | 22-Jul-13 | 28-Jul-10 |  | 
Closure | 29-Jul-13 | 29-Jul-10 |  | 

## Slide 17
GMSC Erlang Licenses
13-3G-COR12
Project Title/ID
Start Date: 28-Feb-13
Completion Date: 29-Aug-13
Timeline / ETC
Issues / Risks
Description / Comments
Licenses in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Increase the licenses GMSC Erlang on the CORE equipment.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 28-Feb-13 | 06-Mar-13 | 22-Mar-13 | Closed
Product register in Oracle | 07-Mar-13 | 20-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 21-Mar-13 | 03-Apr-13 | 22-Mar-13 | Closed
PO Date | 04-Apr-13 | 10-Jul-13 |  | On going
Delivery equipment Date | 11-Jul-13 | 11-Jul-13 |  | 
Kick Off | 11-Jul-13 | 18-Jul-13 |  | 
Start project | 19-Jul-13 | 21-Aug-13 |  | 
On production | 22-Aug-13 | 28-Aug-13 |  | 
Closure | 29-Aug-13 | 29-Aug-13 |  | 

## Slide 18
GMGW Channel Licenses
13-3G-COR013
Project Title/ID
Start Date:
Completion Date:
Timeline / ETC
Issues / Risks
Description / Comments
Licenses in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issue: Delay in the acquisition process Actions: Admon Delivery Excellence have the request to upload the requisition on Oracle
back
Project Manager: Marcos Trujillo
Increase licenses for GMGW Channels in Guadalajara, Leon, Acapulco, Puebla, Queretaro, Toluca, Cancun, Monterrey and San Luis Potosi
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 25-Feb-13 | 03-Mar-13 | 22-Mar-13 | Closed
Product register in Oracle | 04-Mar-13 | 17-Mar-13 | 22-Mar-13 | Closed
Requisition Date | 18-Mar-13 | 31-Mar-13 | 22-Mar-13 | Closed
PO Date | 01-Apr-13 | 07-Jul-13 |  | On Going
Delivery equipment Date | 08-Jul-13 | 14-Jul-13 |  | 
Kick Off | 15-Jul-13 | 22-Jul-13 |  | 
Start project | 23-Jul-13 | 25-Aug-13 |  | 
On production | 26-Aug-13 | 01-Sep-13 |  | 
Closure | 02-Sep-13 | 02-Sep-13 |  | 

## Slide 19
Civil Work Smithy
13-ID-FLM013
Project Title/ID
Start Date: 20-Mar-13
Completion Date: 30-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Services Civil Work in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issues: delays in seeking Requisition Actions: be revised in meeting with Juan Perez Risks: delays in seeking Requisition For Services contractor
Actions: follow-up will be given on Wednesdays meetings
back
Project Manager: Marcos Trujillo
Smithy adjustments Civil Work: CONSTRUCTION - EXTERNAL WORK - WORK, AS FENCES, FENCES, STAIRS, ETC.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Product register in Oracle | 23-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Requisition Date | 23-Feb-13 | 23-Mar-13 | 22-Mar-13 | Close
PO Date | 25-Mar-13 | 26-Mar-13 |  | Delay
Delivery equipment Date | 19-Apr-13 | 20-Apr-13 |  | Open
Kick Off | 23-Apr-13 | 23-Apr-13 |  | Open
Start project | 24-Apr-13 | 04-Jul-13 |  | Open
On production | 04-Jul-13 | 04-Jul-13 |  | Open
Closure | 05-Jul-13 | 05-Jul-13 |  | Open

## Slide 20
Swap HVAC 5TR (Increase thermal load)
13-ID-FLM012
Project Title/ID
Start Date: 18-Feb -13
Completion Date: 30-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Swap HVAC 5TR in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issues: delays in seeking Requisition Actions: be revised in meeting with Juan Perez Risks: compliance dates for terminals this project depend on the delivery of the equipment in the country
Actions: follow-up will be given on Wednesdays meetings
back
Project Manager: Marcos Trujillo
Swap HVAC 5TR (Increase thermal load) HVAC INSTALLATION LOT. THAT HAS 2 AIR CONDITIONING EQUIPMENT
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Product register in Oracle | 23-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Requisition Date | 23-Feb-13 | 23-Mar-13 | 22-Mar-13 | Close
PO Date | 25-Mar-13 | 26-Mar-13 |  | Delay
Delivery equipment Date | 19-Apr-13 | 20-Apr-13 |  | Open
Kick Off | 23-Apr-13 | 23-Apr-13 |  | Open
Start project | 24-Apr-13 | 04-Jul-13 |  | Open
On production | 04-Jul-13 | 04-Jul-13 |  | Open
Closure | 05-Jul-13 | 05-Jul-13 |  | Open

## Slide 21
Dam Build
13-ID-FLM014
Project Title/ID
Start Date: 20 Mar-13
Completion Date: 30 Jun-13
Timeline / ETC
Issues / Risks
Description / Comments
Services Work in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issues: delays in seeking Requisition Actions: be revised in meeting with Juan Perez Risks: delays in seeking Requisition For Services contractor
Actions: follow-up will be given on Wednesdays meetings
back
Project Manager: Marcos Trujillo
Dam Build: CONSTRUCTION - EXTERNAL WORK - WORK, AS FENCES, FENCES, STAIRS, ETC.
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Product register in Oracle | 23-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Requisition Date | 23-Feb-13 | 23-Mar-13 | 22-Mar-13 | Close
PO Date | 25-Mar-13 | 26-Mar-13 |  | Delay
Delivery equipment Date | 19-Apr-13 | 20-Abr-13 |  | Open
Kick Off | 23-Apr-13 | 23-Abr-13 |  | Open
Start project | 24-Apr-13 | 04-Jul-13 |  | Open
On production | 04-Jul-13 | 04-Jul-13 |  | Open
Closure | 05-Jul-13 | 05-Jul-13 |  | Open

## Slide 22
Coax Cable Protection
13-ID-FLM015
Project Title/ID
Start Date: 18-Feb-13
Completion Date: 30-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Services Work in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issues: delays in seeking Requisition Action: be revised in meeting with Juan Perez Risks: this project depends on the delivery of services to vender to requisition the suitability of the site
Actions: follow-up will be given on Wednesdays meetings
back
Project Manager: Marcos Trujillo
Coax Cable Protection : COAXIAL LINE PROTECTION IN TOWER
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Product register in Oracle | 23-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Requisition Date | 23-Feb-13 | 23-Mar-13 | 22-Mar-13 | Close
PO Date | 25-Mar-13 | 26-Mar-13 |  | Delay
Delivery equipment Date | 19-Apr-13 | 20-Apr-13 |  | Open
Kick Off | 23-Apr-13 | 23-Apr-13 |  | Open
Start project | 24-Apr-13 | 04-Jul-13 |  | Open
On production | 04-Jul-13 | 04-Jul-13 |  | Open
Closure | 05-Jul-13 | 05-Jul-13 |  | Open

## Slide 24
Generator 35 KW & TS Relocation
13-ID-FLM016
Project Title/ID
Start Date: 18-Feb-13
Completion Date: 30-Jul-13
Timeline / ETC
Issues / Risks
Description / Comments
Services Work in requisition by NSN
Complete Activities
Validate with Juan Perez the priority between IDEN and 3G projects
Next Steps
Milestones and Key Dates
Issues: delays in seeking Requisition Actions: be revised in meeting with Juan Perez Risks: compliance dates for close this project depend on the delivery of the equipment in the country
Actions: follow-up will be given on Wednesdays meetings
back
Project Manager: Marcos Trujillo
Generator 35 KW & TS Relocation: Relocation & TS 35KW generator
Milestone / Activity | Start | End | Revised End | Status
Final BoQ Final | 20-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Product register in Oracle | 23-Feb-13 | 22-Feb-13 | 22-Mar-13 | Close
Requisition Date | 23-Feb-13 | 23-Mar-13 | 22-Mar-13 | Close
PO Date | 25-Mar-13 | 26-Mar-13 |  | Delay
Delivery equipment Date | 19-Apr-13 | 20-Apr-13 |  | Open
Kick Off | 23-Apr-13 | 23-Apr-13 |  | Open
Start project | 24-Apr-13 | 04-Jul-13 |  | Open
On production | 04-Jul-13 | 04-Jul-13 |  | Open
Closure | 05-Jul-13 | 05-Jul-13 |  | Open